## Read me
Estimate upload template
One workbook carries any number of estimates. Fill the three data sheets; leave this sheet as it is. Blue cells are yours to fill.
Sheet 'Estimates' — one row per estimate.
estimate_id required. Your estimating system's id (e.g. EST6115758). Rows are matched and updated by this id, never by name.
estimator, client, jobsite optional text. The platform never links a client by name.
name required. Estimate / project name.
status required. Pending, Sold or Lost. Any other word is loaded without a normalized status and reported.
price required. The estimate's total price: the control total. Kept work areas on 'Work areas' must sum to it.
estimate_date optional. YYYY-MM-DD.
Sheet 'Work areas' — one row per work area (the schedule-of-values line the customer sees and that billing refers to as #n).
estimate_id, order required. order is the line number; it is the work area's identity across versions — never renumber.
kept required. Y or N. N = omitted from the contract. An omitted work area, or one priced 0.00, needs no cost lines.
name required. A name beginning 'CO:' or 'C/O' suggests a change order; a person confirms it.
price required. notes optional.
Sheet 'Estimate costs' — one or more rows per kept work area, each with exactly one cost code.
estimate_id, order required; must match a row on 'Work areas'.
cost_code required. Three digits: division digit + cost-type slot (e.g. 210 = EX Labor, 240 = EX Subcontractors). The code equals the ledger account without its leading 5.
hours optional. Estimated labor (or machine) hours for the line.
amount required. Estimated cost. A work area's cost is the sum of its lines; the estimate's cost by category is the sum over kept work areas.
notes optional. What the line is made of.
Money to the cent. A kept work area with no cost line leaves the estimate outside the WIP schedule until a person adds the lines (D-04).
Re-uploading the same file changes nothing; a changed file creates a new version and the earlier one is kept.
Worked example: EST6115758, 67 Elm Street ¦ Parking Lot, coded as an EX (excavation) estimate. Work area 5 has a placeholder line (290) because its item detail was not available; work area 17 is omitted and has no cost lines.
Control checks (recalculated when the file is opened)
estimate_id | price on 'Estimates' | kept work-area prices | difference | cost lines total | kept work areas without a cost line
EST6115758 | 475129.68 | 475129.68 | 0 | 315832.69 | 0
Estimated cost by cost category (kept work areas), with the WIP-basis treatment under D-04
cost_code | cost category | amount | in WIP basis (D-04)
210 | Labor | 32585.55 | Yes
220 | Labor Burden | 0 | Not decided (D-05)
230 | Materials | 63940.8 | Yes
235 | Supplies | 0 | Yes
240 | Subcontractors | 132965 | Yes
245 | Equipment (owned) | 14589.7 | No
247 | Vehicles (owned) | 14608.79 | No
250 | Equipment Rental | 10491.5 | Yes
255 | Equipment Maintenance | 0 | No
260 | Disposal | 0 | Yes
265 | Fuel | 0 | No
270 | Permits & Bonds | 120 | Yes
280 | Warranty | 0 | Not decided (D-04)
290 | Other | 46531.35 | Yes
| Total estimated cost | 315832.69
| EAC in the WIP basis | 286634.2
Labor Burden (220) is in the basis only if D-05 puts it on both sides; Warranty (280) is not decided (D-04). Work area 5's placeholder sits in 290 until split.

## Estimates
estimate_id | estimator | client | jobsite | name | status | price | estimate_date
EST6115758 |  |  |  | 67 Elm Street ¦ Parking Lot | Sold | 475129.68
Note on A2: Worked example. price = the estimating system's Total Price (kept work areas). Estimator, client, jobsite and date left for the owner.

## Work areas
estimate_id | order | kept | name | price | notes
EST6115758 | 1 | Y | Mobilization | 5500
EST6115758 | 2 | Y | Erosion Control & Site Prep | 10830.68
EST6115758 | 3 | Y | Demo Existing Wall | 17142.92
EST6115758 | 4 | Y | New Retaining Wall | 132820.88
EST6115758 | 5 | Y | Underground Detention System | 73049.39
EST6115758 | 6 | Y | Drainage Structures & Piping | 35233.92
EST6115758 | 7 | Y | Drainage Connection in Street | 12044.03
EST6115758 | 8 | Y | Grading & Pavement Prep | 37409.43
EST6115758 | 9 | Y | Pavement | 52624
EST6115758 | 10 | Y | Striping & Signage | 4042.39
EST6115758 | 11 | Y | Granite Curb | 23627.5
EST6115758 | 12 | Y | Sidewalk Prep | 11825.46
EST6115758 | 13 | Y | Concrete Sidewalk | 23025.4
EST6115758 | 14 | Y | Concrete Steps & Handrail | 6971.88
EST6115758 | 15 | Y | Landscaping | 12773.71
EST6115758 | 16 | Y | Chain Link Fence | 6548
EST6115758 | 17 | N | Budget for Adjacent Property Repairs (if needed) | 15000
EST6115758 | 18 | Y | CO: Ledge Removal per Day | 5475
EST6115758 | 19 | Y | CO: Permitting | 499.4
EST6115758 | 20 | Y | CO: Water/Sewer Cap & Inspections | 0
EST6115758 | 21 | Y | CO: Parking Extension 8/24-8/28 2 loads gravel 4-24s 4-caps | 3685.69
Note on C18: Order 17 is ticked Keep/Omit in LMN: omitted, kept = N. Its 15,000.00 is outside the control total and it has no cost lines.

## Estimate costs
estimate_id | order | cost_code | hours | amount | notes
EST6115758 | 1 | 210 | 8 | 386.83 | Average crew cost
EST6115758 | 1 | 247 | 10 | 726.19 | Driver flat rate w/ truck
EST6115758 | 1 | 245 |  | 162.1 | Heavy tag trailer
EST6115758 | 1 | 250 |  | 260 | Portable toilet
EST6115758 | 1 | 250 |  | 2735 | Mobile fencing rental
EST6115758 | 2 | 210 | 18 | 863.46 | Crew 435.18, operator 428.28
EST6115758 | 2 | 247 | 10 | 804.5 | Crew truck 150.93, driver 653.57
EST6115758 | 2 | 245 |  | 505.26 | CAT 316
EST6115758 | 2 | 250 |  | 1440 | Bulldozer rental
EST6115758 | 2 | 230 |  | 2104.4 | Crushed stone 750.00, fabric 40.00, silt sock 966.40, sediment bags 348.00
EST6115758 | 2 | 240 |  | 1500 | Haight Engineering survey/layout
EST6115758 | 3 | 210 | 83 | 4412.02 | Crew 1305.55, laborer 994.71, manager 126.94, operator 1284.93 (adjusted to tie)
EST6115758 | 3 | 247 | 27 | 2413.51 | Crew truck 452.79, driver 1960.72
EST6115758 | 3 | 245 |  | 3350.78 | CAT 316 1515.78, CAT 930M 674.91, Kubota 357 w/ hammer 1500.00 (Kubota may be rental), Mecalac 360.09
EST6115758 | 4 | 210 | 135 | 5975.15 | Crew 2175.92, laborer 1657.85, operator 2141.38
EST6115758 | 4 | 247 | 50 | 4022.51 | Crew truck 754.65, driver 3267.86
EST6115758 | 4 | 245 |  | 3846 | CAT 316 2245.60, Mecalac 1600.40
EST6115758 | 4 | 230 |  | 13300 | Bank run gravel 1400.00, stone 7920.00, rip rap 1680.00, HDPE pipe 1500.00, fitting 50.00, fabric 750.00
EST6115758 | 4 | 240 |  | 60170 | Gravity retaining wall, Pepin Precast
EST6115758 | 5 | 290 |  | 46381.35 | PLACEHOLDER: item detail not in the PDF; owner splits from LMN
EST6115758 | 6 | 210 | 102 | 5541.73 | Crew 1740.74, laborer 1326.28, manager 761.62, operator 1713.10 (adjusted to tie)
EST6115758 | 6 | 247 | 14 | 1329.91 | Crew truck 603.72, driver 726.19
EST6115758 | 6 | 245 |  | 3800.7 | CAT 316 1010.52, CAT 930M 1349.82, Mecalac 1440.36
EST6115758 | 6 | 250 |  | 958.5 | Vibratory roller rental
EST6115758 | 6 | 230 |  | 10043 | Stone 1728.00, culvert pipe 2360.00, catch basins 3455.00, manholes 2500.00
EST6115758 | 7 | 210 | 30 | 1385.44 | Crew 435.18, laborer 331.57, manager 190.40, operator 428.28 (adjusted to tie)
EST6115758 | 7 | 247 | 9 | 731.88 | Crew truck 150.93, driver 580.95
EST6115758 | 7 | 245 |  | 360.09 | Mecalac
EST6115758 | 7 | 230 |  | 1728 | Gravel base 432.00, stone 432.00, culvert pipe 864.00
EST6115758 | 7 | 240 |  | 3700 | All Phase Paving, patch
EST6115758 | 8 | 210 | 150 | 6927.16 | Crew 2175.92, laborer 1657.85, manager 952.02, operator 2141.38 (adjusted to tie)
EST6115758 | 8 | 247 | 35 | 2933.23 | Crew truck 754.65, driver 2178.58
EST6115758 | 8 | 245 |  | 1122.8 | CAT 316
EST6115758 | 8 | 250 |  | 3198 | Bulldozer rental 1920.00, vibratory roller rental 1278.00
EST6115758 | 8 | 230 |  | 8600 | Crushed bank run 1400.00, gravel base 7200.00
EST6115758 | 9 | 240 |  | 43010 | All Phase Paving: binder 26565.00, top coat 16445.00
EST6115758 | 10 | 210 | 12 | 610.47 | Crew 483.54, manager 126.94 (adjusted to tie)
EST6115758 | 10 | 240 |  | 1950 | Signs/signage 750.00, Tri State Striping 1200.00
EST6115758 | 11 | 210 | 18 | 870.37 | Crew
EST6115758 | 11 | 230 |  | 17470 | Granite curb cut-to-fit 11744.00 + 741.00 + 2640.00, freight 850.00, concrete Hissong 1495.00
EST6115758 | 12 | 210 | 72 | 3253.51 | Crew 1305.55, laborer 663.14, operator 1284.93 (adjusted to tie)
EST6115758 | 12 | 247 | 9 | 888.51 | Crew truck 452.79, driver 435.72
EST6115758 | 12 | 245 |  | 960.24 | Mecalac
EST6115758 | 12 | 230 |  | 1890 | Gravel base
EST6115758 | 13 | 240 |  | 12810 | Concrete sidewalk installed, 1830 SF
EST6115758 | 13 | 230 |  | 1600 | Detectable warning strips
EST6115758 | 14 | 240 |  | 4825 | Concrete steps installed 1350.00, Brentwood Fence handrail 3475.00
EST6115758 | 15 | 210 | 27 | 1305.55 | Crew
EST6115758 | 15 | 247 | 10 | 525.37 | Crew truck 150.93, dump truck 6-wheeler 173.04, dump truck tri-axle 201.40
EST6115758 | 15 | 245 | 5 | 161.65 | Mini excavator
EST6115758 | 15 | 230 |  | 5079 | Loam 864.00, plant budget (derived to tie), fertilizer 65.00, mulch 540.00, delivery 125.00, hydroseed 180.00
EST6115758 | 16 | 240 |  | 5000 | Brentwood Fence, 200 LF chain link
EST6115758 | 18 | 210 | 18 | 863.46 | Crew 435.15, operator 428.28 (adjusted to tie)
EST6115758 | 18 | 247 | 1 | 233.18 | Crew truck 150.93, tri-axle dump 82.25
EST6115758 | 18 | 245 |  | 320.08 | Mecalac
EST6115758 | 18 | 250 |  | 1900 | Rental excavator w/ 8K hammer
EST6115758 | 18 | 290 |  | 150 | Standard mobilization
EST6115758 | 19 | 270 |  | 120 | Driveway permit 50.00, trench permit 70.00, wall permit 0.00
EST6115758 | 19 | 210 | 3 | 190.4 | Excavation manager
EST6115758 | 21 | 230 |  | 2126.4 | Gravel base 450.00, stone 1166.40, wall block 460.00 + 50.00
Note on C2: Codes shown are the EX division (2xx). The dropdown lists EX only for the example; the platform validates against the tenant's full cost-code grid (LS 1xx, EX 2xx, GC 3xx, SNOW 4xx).